## Summary
| Overall progress of the QA cycle(Ontime, delayed, Stopped) | On time
| Total number of test cases | 102
| Number of testers | 5
| Test cycle duration | 4 days
Status for 2024-03-23
| Number of test cases planned | 102 | The gap in the total executed and planned can be absorbed by the QA team
| Number of test cases executed | 87
| Number of test cases executed overall | 87
| Number of defects encountered today | 13
| Number of defect encountered so far | 13
| Number of critical defects- still open | 13
Overall status
| Number of test cases planned | 102
| Number of test cases executed | 87
| Number of test cases failed | 19
| Total Defects | 13
| Critical defects percentage | 68%
©- SoftwareTestingHelp.com

## Swapna - status
Module | Test Case | Scenario | Complexity | Responsible tester | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed) | Defect ID- Brief description | Severity | Status
User | User Login | Verify TravelApp user login page loads successfully | Simple | Swapna Tambe | 2024-03-20 | Pass
User | User Login | User Login with valid username and valid Password | Medium | Swapna Tambe | 2024-03-20 | Pass
User | User Login | User Login with invalid username and invalid Password | Medium | Swapna Tambe | 2024-03-20 | Pass
User | User Login | User Login with valid username and Invalid Password | Medium | Swapna Tambe | 2024-03-20 | Pass
User | User Login | User Login with invalid username and valid Password | Medium | Swapna Tambe | 2024-03-20 | Pass
User | User Login | User Login with empty user id and valid Password | Medium | Swapna Tambe | 2024-03-20 | Pass
User | User Login | User Login with valid username and empty Password | Medium | Swapna Tambe | 2024-03-21 | Pass
User | User Login | User Login with empty login credentials | Medium | Swapna Tambe | 2024-03-21 | Pass
User | User Login | Verify user is redirected to the login page after an invalid login attempt by using the "Back" option from the error page. | Medium | Swapna Tambe | 2024-03-21 | Fail | 00001- User is not redirected to the login page after an invalid login attempt by using the "Back" link option from the error page. 404 error on clicking the link | High | Open
User | User Login | Reset the login credentials by clicking the Clear button | Medium | Swapna Tambe | 2024-03-21 | Pass
User | Give Feedback | Verify Give Feedback page loads successfully | Medium | Swapna Tambe | 2024-03-22 | Pass
User | Give Feedback | Give feedback by submitting valid email address and feedback message | Medium | Swapna Tambe | 2024-03-22 | Pass
User | Give Feedback | Give feedback by submitting invalid email address format and feedback message | Complex | Swapna Tambe | 2024-03-22 | Fail | 00002 -Feedback gets accepted for invalid email address format for your emaild Id field. User is able to submit the feedback with incorrect email address format | Medium | Open
User | Give Feedback | Give feedback by submitting only email address and empty feedback message | Complex | Swapna Tambe | 2024-03-22 | Pass
User | Give Feedback | Give feedback by submitting only feedback message and empty email address. | Complex | Swapna Tambe | 2024-03-22 | Pass
User | Give Feedback | Give feedback by submit feedback with empty email id and empty feedback message | Complex | Swapna Tambe | 2024-03-22 | Pass
User | Give Feedback | Reset the email id and feedback message using clear button | Complex | Swapna Tambe | 2024-03-22 | Pass
User | View Feedback | Verify View Feedback page loads successfully | Simple | Swapna Tambe | 2024-03-23 | Pass
User | View Feedback | View feedback on testimonial Page | Medium | Swapna Tambe | 2024-03-23 | Pass
User | View Feedback | View feedbacks on testomonials strip on testomonials page | Medium | Swapna Tambe | 2024-03-23 | Pass
User | View Routes | verify user can view all available routes | Simple | Bidushi Kabir | 23-03-2024 | Pass
User | View Routes | verify user can view PickUp Points of a particular route | Medium | Bidushi Kabir | 23-03-2024 | Pass
User | Book Tickets | Verify user can check tickets availability with valid information | Simple | Bidushi Kabir | 23-03-2024 | Pass
User | Book Tickets | Verify user cannot check tickets availability with invalid information | Simple | Bidushi Kabir | 23-03-2024 | Pass
User | Book Tickets | Verify user can select bus and book tickets | Medium | Bidushi Kabir | 23-03-2024 | Pass
User | Book Tickets | Verify user can continue with valid seat selection | Medium | Bidushi Kabir | 23-03-2024 | Pass
User | Book Tickets | Verify user cannot continue with invalid seat selection | Medium | Bidushi Kabir | 23-03-2024 | Pass
User | Book Tickets | Verify user can save customer information with valid details | Medium | Bidushi Kabir | 23-03-2024 | Pass
User | Book Tickets | Verify user cannot save customer information with invalid details | Medium | Bidushi Kabir | 23-03-2024 | Pass
User | Book Tickets | Verify user can continue to payment with saved customer info | Medium | Bidushi Kabir | 23-03-2024 | Pass
User | Book Tickets | Verify user cannot continue to payment with unsaved customer info | Medium | Bidushi Kabir | 23-03-2024 | Pass
User | Book Tickets | Verify user can save payment details with valid information | Complex | Bidushi Kabir | 23-03-2024 | Pass
User | Book Tickets | Verify user cannot save payment details with invalid information | Complex | Bidushi Kabir | 23-03-2024 | Pass
User | Book Tickets | Verify user can confirm payment with saved payment details | Complex | Bidushi Kabir | 23-03-2024 | Pass
User | Book Tickets | Verify user cannot confirm payment with unsaved payment details | Complex | Bidushi Kabir | 23-03-2024 | Pass
User | Book Tickets | Verify user can print ticket after viewing travel details | Complex | Bidushi Kabir | 23-03-2024 | Pass
User | Book Tickets | Verify user can use pop-up window to print the ticket details | Complex | Bidushi Kabir | 23-03-2024 | Pass
User | Cancel Tickets | Verify user can find the ticket with valid ticket ID | Simple | Bidushi Kabir | 23-03-2024 | Pass
User | Cancel Tickets | Verify user cannot find the ticket with invalid ticket ID | Medium | Bidushi Kabir | 23-03-2024 | Pass
User | Cancel Tickets | Verify user can cancel the ticket after viewing the ticket details | Complex | Bidushi Kabir | 23-03-2024 | Pass
Admin | Admin Login | Verify TravelApp admin login page loads successfully | Simple | Rupal Patel | 2024-03-19 | Pass
Admin | Admin Login | verify admin Login with valid username and valid Password | Medium | Rupal Patel | 2024-03-19 | Pass
Admin | Admin Login | verify admin Login with valid username and Invalid Password | Medium | Rupal Patel | 2024-03-19 | Pass
Admin | Admin Login | Verify admin Login with Invalid username and valid Password | Medium | Rupal Patel | 2024-03-19 | Pass
Admin | Admin Login | Verify admin Login with Invalid username and Invalid Password | Medium | Rupal Patel | 2024-03-19 | Pass
Admin | Admin Login | Verify admin Login with empty admin id and valid Password | Medium | Rupal Patel | 2024-03-19 | Pass
Admin | Admin Login | Verify admin Login with valid admin id and empty Password | Medium | Rupal Patel | 2024-03-19 | Pass
Admin | Admin Login | Verify admin Login without login credentials | Medium | Rupal Patel | 2024-03-19 | Pass
Admin | Admin Login | Verify Reset link by clicking on the reset button | Medium | Rupal Patel | 2024-03-19 | Pass
Admin | Admin Logout | Verify admin logout button | Complex | Rupal Patel | 2024-03-25 | Not executed
Admin | Admin Logout | Verify admin logout and immediate login | Complex | Rupal Patel | 2024-03-25 | Not executed
Admin | Admin Logout | Verify admin logout and browsing back | Complex | Rupal Patel | 2024-03-25 | Not executed
Admin | Add Route Page | Added route for Valid Information | High | Suvidha | 2024-03-20 | Pass
Admin | Add Route Page | Added invalid route for Travel ID is 'R" | Medium | Suvidha | 2024-03-20 | Fail | 00100: Added the route Successfully | High | open
Admin | Add Route Page | Added Invalid route for Bus ID is "R" | Medium | Suvidha | 2024-03-20 | Fail | 00101: Added the route Successfully | High | open
Admin | Add Route Page | Added Invalid route for Departure is '"R" | Medium | Suvidha | 2024-03-21 | Fail | 00102: Added the route Successfully | High | open
Admin | Add Route Page | Addeed Invalid route for Arrival is "R" | Medium | Suvidha | 2024-03-21 | Fail | 00103: Added the route Successfully | High | open
Admin | Add Route Page | Added Invalid route for Fare is "R" | Medium | Suvidha | 2024-03-21 | Fail | 00104: Added the route Successfully | High | open
Admin | Add Route Page | Added Empty Travel ID | Medium | Suvidha | 2024-03-22 | Fail | 00105: Added the route Successfully | Medium | open
Admin | Add Route Page | Reset the route by clicking on the Clear Button | Simple | Suvidha | 2024-03-22 | Pass
Admin | View Route | Verify view route page loads successfully | Simple | Suvidha | 2024-03-25 | Not executed |  | Medium | Open
Admin | View Route | Add Pick up details of perticular Routes With valid Data | Medium |  | 2024-03-25 | Not executed
Admin | View Route | Add Pick Up details of particular Route with invalid BusID | Medium | Suvidha | 2024-03-25 | Not executed
Admin | View Route | Reset the Pick up details by clicking the Clear button | Medium | Suvidha | 2024-03-25 | Not executed
Admin | View Route | View Pick up deatils of perticular route | Medium | Suvidha | 2024-03-25 | Not executed
Admin | Delete Route | Verify Delete Route Page Loads Successfully | Simple | Suvidha | 2024-03-25 | Not executed
Admin | Delete Route | View Route details with valid selection | Medium |  | 2024-03-25 | Not executed
Admin | Delete Route | View Route details with invalid selection | Medium | Suvidha | 2024-03-25 | Not executed
Admin | Delete Route | Delete Routes with valid selection | Medium | Suvidha | 2024-03-25 | Not executed
Admin | Delete Route | Delete Routes with invalid selection | Medium | Suvidha | 2024-03-25 | Not executed
Admin | Add Travel | Verify Add New Travel Page Loads Successfully | Simple | Fan Yang | 2024-03-22 | Pass
Admin | Add Travel | Add a new travel with all valid inputs | Complex | Fan Yang | 2024-03-22 | Pass
Admin | Add Travel | Add a new travel with empty Travels Name | Complex | Fan Yang | 2024-03-22 | Fail | 00010: Expected error message not displayed; instead, 'Travel added successfully' message is shown. | High | Open
Admin | Add Travel | Add a new travel with invalid Travels Name | Complex | Fan Yang | 2024-03-22 | Fail | 00010: Expected error message not displayed; instead, 'Travel added successfully' message is shown. | High | Open
Admin | Add Travel | Add a new travel with empty Address | Complex | Fan Yang | 2024-03-22 | Fail | 00010: Expected error message not displayed; instead, 'Travel added successfully' message is shown. | High | Open
Admin | Add Travel | Add a new travel with invalid Address | Complex | Fan Yang | 2024-03-22 | Fail | 00010: Expected error message not displayed; instead, 'Travel added successfully' message is shown. | High | Open
Admin | Add Travel | Add a new travel with empty Agent Name | Complex | Fan Yang | 2024-03-22 | Fail | 00010: Expected error message not displayed; instead, 'Travel added successfully' message is shown. | High | Open
Admin | Add Travel | Add a new travel with invalid Agent Name | Complex | Fan Yang | 2024-03-22 | Fail | 00010: Expected error message not displayed; instead, 'Travel added successfully' message is shown. | High | Open
Admin | Add Travel | Add a new travel with empty Phone Number | Complex | Fan Yang | 2024-03-22 | Fail | 00010: Expected error message not displayed; instead, 'Travel added successfully' message is shown. | High | Open
Admin | Add Travel | Add a new travel with invalid Phone Number | Complex | Fan Yang | 2024-03-22 | Fail | 00010: Expected error message not displayed; instead, 'Travel added successfully' message is shown. | High | Open
Admin | Add Travel | Reset the travel details by clicking the Clear button | Medium | Fan Yang | 2024-03-22 | Fail | 00010: Expected error message not displayed; instead, 'Travel added successfully' message is shown. | Medium | Open
Admin | View Travels | Verify View Travels Page Loads Successfully | Simple | Fan Yang | 2024-03-22 | Pass
Admin | View Travels | Add bus details of particular travel with all valid inputs | Complex | Fan Yang | 2024-03-22 | Pass
Admin | View Travels | Add bus details of particular travel with empty BusType | Complex | Fan Yang | 2024-03-22 | Pass
Admin | View Travels | Add bus details of particular travel with empty BusNumber | Complex | Fan Yang | 2024-03-22 | Pass
Admin | View Travels | Add bus details of particular travel with invalid BusNumber | Complex | Fan Yang | 2024-03-22 | Fail | 00011: Expected error message not displayed; instead, 'Bus added successfully' message is shown. | High | Open
Admin | View Travels | Reset the bus details by clicking the Clear button | Medium | Fan Yang | 2024-03-22 | Pass
Admin | View Travels | View bus details of particular travel | Medium | Fan Yang | 2024-03-22 | Pass
Admin | Delete Travel | Verify Delete Travel Page Loads Successfully | Simple | Fan Yang | 2024-03-22 | Pass
Admin | Delete Travel | View travel details with valid selection | Medium | Fan Yang | 2024-03-22 | Pass
Admin | Delete Travel | View travel details with invalid selection | Medium | Fan Yang | 2024-03-22 | Pass
Admin | Delete Travel | Delete travel with valid selection | Medium | Fan Yang | 2024-03-22 | Fail | 00012: Expected message not displayed; instead, nothing is shown. | Low | Open
Admin | Delete Travel | Delete travel with invalid selection | Medium | Fan Yang | 2024-03-22 | Pass
Admin/User | Non-Functional | Validate the Response Time | Medium | Rupal Patel | 2024-03-21 | Pass
Admin/User | Non-Functional | Validate Load Testing | Medium | Rupal Patel | 2024-03-21 | Pass
Admin/User | Non-Functional | Validate Stress Testing | Medium | Rupal Patel | 2024-03-21 | Pass
Admin/User | Non-Functional | Validate Recovery Test | High | Rupal Patel | 2024-03-26 | Not executed
Admin/User | Non-Functional | Validate Usability Testing (Ease of switching Modules) | Simple | Rupal Patel | 2024-03-21 | Pass
Admin/User | Non-Functional | Validate Usability Testing | Simple | Rupal Patel | 2024-03-21 | Pass
Admin/User | Non-Functional | Validate Reliability Testing | Medium | Rupal Patel | 2024-03-21 | Pass
Admin/User | Non-Functional | Validate Security Testing | High | Rupal Patel | 2024-03-26 | Not executed
Admin/User | Non-Functional | Browser Compatibility Testing | Simple | Rupal Patel | 2024-03-21 | Pass

## Swapna - bug report
Defect ID | Test Script ID | Defect Description | Steps to reproduce | Severity | State | Created by | Assigned to
00001 | TSC_ULF_09 | User is not redirected to the login page after an invalid login attempt by using the "Back" link option from the error page. 404 error on clicking the link | 1.Navigate to the TravelApp web application 2. Click on 'User Login' 1 3. Give Invalid Login Credentials 4. Click on 'Submit' button 5. On error page use Back option link to get back to Login page Expected Result - User gets back to User login page Actual Result - A 404 error page apperas and TraveApp application has to be relaunched to recover from this state | High | Open | Swapna Tambe | Dev representative
00002 | TSC_UGF_03 | Feedback gets accepted for invalid email address format for your emaild Id field. User is able to submit the feedback with incorrect email address format | 1.Log in to user account of TravelApp web application 2.Access Give Feedback Functionality. 3.Give invalid email address in "Your email Id" field 4.Write feedback message in "Feedback" fied 5.Submit the feedback by clicking submit button Expected Result -User should not be able to submit the feeback message Actual Result- User able to submit the feedback with incorrect email address format | Medium | Open | Swapna Tambe | Dev representative
00010 | TSC_AT_03 | Expected error message not displayed; instead, 'Travel added successfully' message is shown. | 1. Select Location 2. Enter Address 3. Enter Agent Name 4. Enter Phone Number 5. Click Submit Expected result: System displays the error message "Travels Name is mandatory". Actual result: System displays "Travels added Successfully". | High | Open | Fan Yang | Dev representative
| TSC_AT_04 | Expected error message not displayed; instead, 'Travel added successfully' message is shown. | 1. Enter Travels Name 2. Select Location 3. Enter Address 4. Enter Agent Name 5. Enter Phone Number 6. Click Submit Expected result: System displays the error message "Please enter valid Travels Name". Actual result: System displays "Travels added Successfully". | High | Open | Fan Yang | Dev representative
| TSC_AT_05 | Expected error message not displayed; instead, 'Travel added successfully' message is shown. | 1. Enter Travels Name 2. Select Location 3. Enter Agent Name 4. Enter Phone Number 5. Click Submit Expected result: System displays the error message "Address is mandatory". Actual result: System displays "Travels added Successfully". | High | Open | Fan Yang | Dev representative
| TSC_AT_06 | Expected error message not displayed; instead, 'Travel added successfully' message is shown. | 1. Enter Travels Name 2. Select Location 3. Enter Address 4. Enter Agent Name 5. Enter Phone Number 6. Click Submit Expected result: System displays the error message "Please enter valid Address". Actual result: System displays "Travels added Successfully". | High | Open | Fan Yang | Dev representative
| TSC_AT_07 | Expected error message not displayed; instead, 'Travel added successfully' message is shown. | 1. Enter Travels Name 2. Select Location 3. Enter Address 4. Enter Phone Number 5. Click Submit Expected result: System displays the error message "Agent Name is mandatory". Actual result: System displays "Travels added Successfully". | High | Open | Fan Yang | Dev representative
| TSC_AT_08 | Expected error message not displayed; instead, 'Travel added successfully' message is shown. | 1. Enter Travels Name 2. Select Location 3. Enter Address 4. Enter Agent Name 5. Enter Phone Number 6. Click Submit Expected result: System displays the error message "Please enter valid Agent Name". Actual result: System displays "Travels added Successfully". | High | Open | Fan Yang | Dev representative
| TSC_AT_09 | Expected error message not displayed; instead, 'Travel added successfully' message is shown. | 1. Enter Travels Name 2. Select Location 3. Enter Address 4. Enter Agent Name 5. Click Submit Expected result: System displays the error message "Phone Number is mandatory". Actual result: System displays "Travels added Successfully". | High | Open | Fan Yang | Dev representative
| TSC_AT_10 | Expected error message not displayed; instead, 'Travel added successfully' message is shown. | 1. Enter Travels Name 2. Select Location 3. Enter Address 4. Enter Agent Name 5. Enter Phone Number 6. Click Submit Expected result: System displays the error message "Please enter valid Phone Number". Actual result: System displays "Travels added Successfully". | High | Open | Fan Yang | Dev representative
| TSC_AT_11 | Expected error message not displayed; instead, 'Travel added successfully' message is shown. | 1. Enter Travels Name 2. Select Location 3. Enter Address 4. Enter Agent Name 5. Enter Phone Number 6. Click Clear 7. Click Submit Expected result: System displays the error message "Travel information is mandatory". Actual result: System displays "Travels added Successfully". | Medium | Open | Fan Yang | Dev representative
00011 | TSC_VT_05 | Expected error message not displayed; instead, 'Bus added successfully' message is shown. | 1. Click Add 2. Click OK 3. Select BusType 4. Enter BusNumber 5. Click Submit Expected result: System displays the error message "Please enter valid BusNumber". Actual result: System displays "Bus added Successfully". | High | Open | Fan Yang | Dev representative
00012 | TSC_DT_04 | Expected message not displayed; instead, nothing is shown. | 1. Select TRAVELSID 2. Click Delete 3. Click OK Expected result: System displays "Travel deleted successfully". Actual result: nothing displayed | Low | Open | Fan Yang | Dev representative
00100 |  | Added the route Successfully | 1.Log into the add route 2.added invalid route for Travel Id is 'R' Expected Result: A new route not Added, database not updated System displays the error message 'Please enter the Valid travel ID' Actual Result: Route added succesfully | High | open | Suvidha
00101 |  | Added the route Successfully | 1.Log into the add route 2.added invalid route Bus ID is 'R' Expected Result: A new route not Added, database not updated System displays the error message 'Please enter the Valid Bus ID' Actual Result: Route added succesfully | High | open | Suvidha
00102 |  | Added the route Successfully | 1.Log into the add route 2.added invalid route Departure is 'R' Expected Result: A new route not Added, database not updated System displays the error message 'Please enter the Valid Departure' Actual Result: Route added succesfully | High | open | Suvidha
00103 |  | Added the route Successfully | 1.Log into the add route 2.added invalid route Arrival is 'R' Expected Result: A new route not Added, database not updated System displays the error message 'Please enter the Valid Arrival' Actual Result: Route added succesfully | High | open | Suvidha
00104 |  | Added the route Successfully | 1.Log into the add route 2.added invalid route Arrival is 'R' Expected Result: A new route not Added, database not updated System displays the error message 'Please enter the Valid Arrival' Actual Result: Route added succesfully | High | open | Suvidha
00105 |  | Added the route Successfully | 1.Log into the add route 2.added invalid route Arrival is 'R' Expected Result: A new route not Added, database not updated System displays the error message 'Please enter the Valid Arrival' Actual Result: Route added succesfully | Medium | open | Suvidha

## Test Cases By Business Area
Test case execution
Functional Area | Total number of test cases | Number of test cases executed | # of passed test cases | Not run | # of failed test cases | Pending clarification | % of test cases executed | % of test cases passed | % of test cases Failed
User Login | 10 | 10 | 9 |  | 1 |  | 100% | 90% | 10%
View Routes | 2 | 2 | 2 |  |  |  | 100% | 100%
Book Tickets | 15 | 15 | 15 |  |  |  | 100% | 100%
Cancel Tickets | 3 | 3 | 3 |  |  |  | 100% | 100%
Give Feedback | 7 | 7 | 6 |  | 1 |  | 100% | 85.71% | 14.28%
View Feedback | 3 | 3 | 3 |  | 0 |  | 100% | 100%
Admin Login | 9 | 9 | 9 |  |  |  | 100% | 100%
Admin Logout | 3 | 0 | 0 | 3 | 0 |  | 0%
Add Route | 8 | 8 | 2 |  | 6 |  | 100% | 50%
View Routes | 5 | 0 |  | 5 |  |  | 0%
Delete Route | 5 | 0 |  | 5 |  |  | 0%
Add Travel | 11 | 11 | 2 | 0 | 9 |  | 100% | 18.18% | 81.82%
View Travels | 7 | 7 | 6 | 0 | 1 |  | 100% | 85.71% | 14.29%
Delete Travel | 5 | 5 | 4 | 0 | 1 |  | 100% | 80% | 20%
Non Functional | 9 | 7 | 7 | 2 |  |  | 80% | 80%
Defects
Functional area | Critical | High | Medium | Low
User Login |  | 1
Give Feedback |  |  | 1
Add Travel |  | 8 | 1
View Travels |  | 1
Delete Travel |  |  |  | 1